## Board Data
Card Name | Description | List | URL
Update the non-Trello board. https://xula0-my.sharepoint.com/:x:/r/personal/epeguero_xula_edu/_layouts/15/Doc.aspx?sourcedoc=%7BA5313BEA-A08E-4818-B9B3-E9FCD726F3CF%7D&file=trello-board-export%20(1).xlsx&fromShare=true&action=default&mobileredirect=true |  | Product Backlog | https://trello.com/c/kYSww2nw/60-update-the-non-trello-board-https-xula0-mysharepointcom-x-r-personal-epegueroxulaedu-layouts-15-docaspxsourcedoc7ba5313bea-a08e
Finish the README's Final Release Checklist. |  | Product Backlog | https://trello.com/c/BabuzMjC/61-finish-the-readmes-final-release-checklist
As a student I want to be able to see my previous schedules from other semesters | For project release: In student_driver.py Create a menu option to request previous schedule, then print previous schedule of user input year and semester In Student.py Create a method that reads the Transcripts document for the year, semester, course name and credit hours from the past time period of choice. This method should return an error message if the semester or year is out of bounds/incorrectly typed. | MMP | https://trello.com/c/FHUSQTnM/5-as-a-student-i-want-to-be-able-to-see-my-previous-schedules-from-other-semesters
As a dev I want class times to be automatically formatted a certain way |  | MMP | https://trello.com/c/Mw1QjVG1/52-as-a-dev-i-want-class-times-to-be-automatically-formatted-a-certain-way
As a admin I want to be able to create a 19 hour schedule from the available course offerings | In Admin.py: - Create a method that reads the credit hours from the Course Offerings document that the Lead created, to make a 19 hour schedule with least amount of classes. This method should print the courses and their credit hours that would create this schedule. This method should have the course offering doc and a transcript as input In Admin_Driver.py - Add an option to the Admin Menu to create a 19 hour course | MMP | https://trello.com/c/xKO43EVS/59-as-a-admin-i-want-to-be-able-to-create-a-19-hour-schedule-from-the-available-course-offerings
As an admin I want to be able to access student’s transcripts | To be completed by Project Release: Method in Admin.py that creates a transcript given user input (student name, schedule ‌ Method in Admin.py that displays a transcript | MMP | https://trello.com/c/Vvy2wAsp/21-as-an-admin-i-want-to-be-able-to-access-students-transcripts
As a dev I want to be able to display the CRNs in descending order | In the Course class, - Create a method that prints the crns of the courses in descending order. Retrieve the crns from the Courses.csv | MMP | https://trello.com/c/SYMXSJIU/50-as-a-dev-i-want-to-be-able-to-display-the-crns-in-descending-order
As a student I want to export my schedule as a PDF |  | MMP | https://trello.com/c/8Bn4Uvg9/49-as-a-student-i-want-to-export-my-schedule-as-a-pdf
As a designer I want the Admin menu to have Welcome message banner | In admin_driver.py - Add a print Welcome message that prints before the Admin menu option display | MMP | https://trello.com/c/XnanRwtV/34-as-a-designer-i-want-the-admin-menu-to-have-welcome-message-banner
As a designer I want a label for that introduces the student before printing the student information | In the student_driver.py - Add a print message before displaying the student information that says "Displaying [Student Full Name] Information" | MMP | https://trello.com/c/OrCH7YOK/47-as-a-designer-i-want-a-label-for-that-introduces-the-student-before-printing-the-student-information
As a professor I want to be able to assign a grade for a course for each student |  | MMP | https://trello.com/c/KqlN5huU/45-as-a-professor-i-want-to-be-able-to-assign-a-grade-for-a-course-for-each-student
As a dev I want to add basic error messages so users can know when something goes wrong |  | MMP | https://trello.com/c/OysaK7ul/56-as-a-dev-i-want-to-add-basic-error-messages-so-users-can-know-when-something-goes-wrong
A a designer I want the layout to look clean and consistent |  | MMP | https://trello.com/c/FtA0zXMK/55-a-a-designer-i-want-the-layout-to-look-clean-and-consistent
As a dev I want to clean up unused code |  | MMP | https://trello.com/c/DmVACRAJ/54-as-a-dev-i-want-to-clean-up-unused-code
As a tester I want to test that the code runs following only the information given in the rule and requirements documentation | Ensure that the given information is enough for the client to use our app | MMP | https://trello.com/c/PhUoXxnQ/43-as-a-tester-i-want-to-test-that-the-code-runs-following-only-the-information-given-in-the-rule-and-requirements-documentation
As a swe I want to create a new schedule with at most 19 credits |  | MMP | https://trello.com/c/Uf83wNAz/37-as-a-swe-i-want-to-create-a-new-schedule-with-at-most-19-credits
As a designer I want the student major to be displayed with ascii art | In Student.py - Edit display_info method to make the student mahor to be printed with ascii art | MMP | https://trello.com/c/agM3RdhE/38-as-a-designer-i-want-the-student-major-to-be-displayed-with-ascii-art
As a doc/writer I want a updated README about our Release #1 |  | MMP | https://trello.com/c/sj0aheI4/35-as-a-doc-writer-i-want-a-updated-readme-about-our-release-1
As a swe I want to compare the transcript and new schedule and make sure no overlapping |  | MMP | https://trello.com/c/n3CPbZfT/39-as-a-swe-i-want-to-compare-the-transcript-and-new-schedule-and-make-sure-no-overlapping
As a designer I want the professor names to be printed in all capital letters |  | MMP | https://trello.com/c/JVdjal9c/36-as-a-designer-i-want-the-professor-names-to-be-printed-in-all-capital-letters
As a doc/writer I want a requirements doc that explains what is needed to run the code |  | MMP | https://trello.com/c/FKrSq7Oc/31-as-a-doc-writer-i-want-a-requirements-doc-that-explains-what-is-needed-to-run-the-code
As a tester I want to test the Schedule class |  | MMP | https://trello.com/c/jquaIgmT/27-as-a-tester-i-want-to-test-the-schedule-class
As a doc/writer I want a Attendance.csv | For Formatting, - Create csv that has students first and last name. This could be used by professors for attendance | MMP | https://trello.com/c/aHkBT4VV/29-as-a-doc-writer-i-want-a-attendancecsv
As a tester I want to test the Course class | Use unittest to test the methods of the Course | MMP | https://trello.com/c/jfghx4wt/22-as-a-tester-i-want-to-test-the-course-class
As a tester I want to test the Professor class |  | MMP | https://trello.com/c/N68YFu3x/25-as-a-tester-i-want-to-test-the-professor-class
As a tester I want to test the Admin class |  | MMP | https://trello.com/c/ALpCOgxF/24-as-a-tester-i-want-to-test-the-admin-class
As a tester I want to test the Student class | Use unittest to test the methods of the Student class | MMP | https://trello.com/c/aDLxZrgD/23-as-a-tester-i-want-to-test-the-student-class
As a professor I want to view which students are in my class |  | MMP | https://trello.com/c/KL1iqaug/8-as-a-professor-i-want-to-view-which-students-are-in-my-class
As a dev I want a Schedule class |  | MMP | https://trello.com/c/sDhKexS1/13-as-a-dev-i-want-a-schedule-class
As a dev I want a professor class |  | MMP | https://trello.com/c/1z4i8rVU/15-as-a-dev-i-want-a-professor-class
As a dev I would like to be able to create a course to assign to a professor and/or students. | All of this will save in the data base | MMP | https://trello.com/c/KXy9P9R5/20-as-a-dev-i-would-like-to-be-able-to-create-a-course-to-assign-to-a-professor-and-or-students
As a professor I want to be able to edit the new schedule being given to students |  | MMP | https://trello.com/c/VbSIcLld/42-as-a-professor-i-want-to-be-able-to-edit-the-new-schedule-being-given-to-students
As a designer I want the fiscal clearance label to be printed in all capital letters | In the Student.py - Update the display_info to make "fiscally cleared" to print as "FISCALLY CLEARED" | MMP | https://trello.com/c/Bp3v6VZj/40-as-a-designer-i-want-the-fiscal-clearance-label-to-be-printed-in-all-capital-letters
As a professor I want to be able to create assignments |  | MMP | https://trello.com/c/dCr1CWXt/33-as-a-professor-i-want-to-be-able-to-create-assignments
As a student I want to log in using my Xula account to see my courses |  | MMP | https://trello.com/c/iWUIWHMv/3-as-a-student-i-want-to-log-in-using-my-xula-account-to-see-my-courses
As the team lead I want to make sure everyone knows how to issue a pull request |  | MMP | https://trello.com/c/lrVMS9XE/9-as-the-team-lead-i-want-to-make-sure-everyone-knows-how-to-issue-a-pull-request
As a lead I want to have a meeting before the release #2 due date to make sure that at least half the tasks are finished |  | MMP | https://trello.com/c/0hzPEgES/53-as-a-lead-i-want-to-have-a-meeting-before-the-release-2-due-date-to-make-sure-that-at-least-half-the-tasks-are-finished
As a student i would like to complete assignment |  | MMP | https://trello.com/c/2Mh7kDYH/44-as-a-student-i-would-like-to-complete-assignment
As a Team lead i would like to make sure everyone is on track |  | MMP | https://trello.com/c/AA1iJetD/48-as-a-team-lead-i-would-like-to-make-sure-everyone-is-on-track
As a dev i want to have a security pin for each professors and admin |  | Done | https://trello.com/c/ooB2slkg/17-as-a-dev-i-want-to-have-a-security-pin-for-each-professors-and-admin
As a dev I want a Student class | Talk about what needs to be in the Student class | Done | https://trello.com/c/SeYSiLyG/10-as-a-dev-i-want-a-student-class
As a dev I want a University Database.csv |  | Done | https://trello.com/c/enfY6h7O/16-as-a-dev-i-want-a-university-databasecsv
As an admin I want to log in using my admin XULA Account to change the time of a course offering |  | Done | https://trello.com/c/5nMDyX9d/6-as-an-admin-i-want-to-log-in-using-my-admin-xula-account-to-change-the-time-of-a-course-offering
As a student I want to be able to register for my XULA account. Entering Name, email, Password, etc. |  | Done | https://trello.com/c/XBW1E1HM/7-as-a-student-i-want-to-be-able-to-register-for-my-xula-account-entering-name-email-password-etc
As a dev I want an Admin class |  | Done | https://trello.com/c/l5vylPwt/12-as-a-dev-i-want-an-admin-class
As a dev I need to update the driver with the mvp stories and cases |  | Done | https://trello.com/c/7EsWXoHH/11-as-a-dev-i-need-to-update-the-driver-with-the-mvp-stories-and-cases
As a an advisor I want to log in using my admin XULA account so that all my advisees schedules will load |  | Done | https://trello.com/c/wELRbMie/4-as-a-an-advisor-i-want-to-log-in-using-my-admin-xula-account-so-that-all-my-advisees-schedules-will-load
As a dev I want a Course class |  | Done | https://trello.com/c/DhxuAJoP/14-as-a-dev-i-want-a-course-class
As a dev I want to be able to have a menu for the admin |  | Done | https://trello.com/c/WDbwvNk0/18-as-a-dev-i-want-to-be-able-to-have-a-menu-for-the-admin
As a doc/writer I want a summary doc that summarizes the accomplishments of Release #1 |  | Done | https://trello.com/c/RoDekuS9/32-as-a-doc-writer-i-want-a-summary-doc-that-summarizes-the-accomplishments-of-release-1
As an advisor I want to be able to change fiscal clearance |  | Done | https://trello.com/c/7eTkyBua/26-as-an-advisor-i-want-to-be-able-to-change-fiscal-clearance
As a lead I want to make a file structure for my team |  | Done | https://trello.com/c/N1qy2Ozi/28-as-a-lead-i-want-to-make-a-file-structure-for-my-team
As a student I would like to see my fiscal clearance |  | Done | https://trello.com/c/OnfotaMf/41-as-a-student-i-would-like-to-see-my-fiscal-clearance
As the lead I want an SDD doc | Due in aedwardsxula repo on 11/23 | Done | https://trello.com/c/xFtS2qgD/57-as-the-lead-i-want-an-sdd-doc
As a doc/writer i want to have at least 20 course offerings |  | Done | https://trello.com/c/oXLU7ddW/58-as-a-doc-writer-i-want-to-have-at-least-20-course-offerings
As a doc/writer I want a updated README about our Release #2 |  | Done | https://trello.com/c/bZH6nTLh/30-as-a-doc-writer-i-want-a-updated-readme-about-our-release-2